## backlog
Sprint | Name | Points | Type | Status | Theme | Description
Sprint 1 | Claims - Big Picture | 1 | SPIKE | Completed | Security | https://app.pluralsight.com/library/courses/claims-based-identity-big-picture
| Active Directory Programming | 2 | SPIKE | Completed | Security | https://app.pluralsight.com/library/courses/active-directory-programming
| Oauth 2 Introduction | 2 | SPIKE | Completed | Security | https://app.pluralsight.com/library/courses/oauth2-json-web-tokens-openid-connect-introduction
| Oauth ASP Api | 5 | SPIKE | Completed | Security | https://app.pluralsight.com/library/courses/oauth-secure-asp-dot-net-api
| Oauth, ASP, Angular | 5 | SPIKE | Completed | Security | https://app.pluralsight.com/library/courses/oauth2-openid-connect-angular-aspdotnet
Sprint 2 | SMWU Bugs | 1 | Task | Completed | Technical Debt | Fix the adding of blank rows.
| Identity Server 4 + asp.core | 1 | SPIKE | Completed | Security | In order to create a proper POC, a simple identity server must be built in Identity Server 4 with asp.core; it must support access token, implicit, and resource owner flows
| Angular 2 implicit/resource owner flow | 1 | SPIKE | Completed | Security | In order to create a proper POC, 2 angular clients must be created, which can log in using either the implicit or resource owner flow.
| Angular 2 token management | 1 | SPIKE | Completed | Security | In order to create a proper POC, an angular client must be created which can handle expired tokens for both implicit and resource owner flows.
| Refresh tokens | 1 | SPIKE | Completed | Security | In order to create a proper POC, clients must be created that can refresh their tokens; both resource owner and access token flows must be supported
| Redirect tokens (implicit) | 1 | SPIKE | Completed | Security | In order to create a proper POC, a client must be created that can get a new token through redirection; when using the implicit flow.
| Login redirects | 1 | SPIKE | Completed | Security | In order to create a proper POC, clients must be created that can redirect to an application page after login; for resource owner, implicit, and access token flows.
| Logout redirects | 1 | SPIKE | Completed | Security | In order to create a proper POC, clients must be created that can redirect the user to the applications login page; for resource owner, implicit, and access token flows.
| Single sign-out | 1 | SPIKE | Completed | Security | In order to create a proper POC, clients must be created that force all other clients to log out; in resource owner, implitic, and access token flows.
| Facebook login | 1 | SPIKE | Completed | Security | In order to create a proper POC, the identity server must be able to authenticate, link, and create users for a facebook account; must support resource owner, implicit, and access token flows.
| Google login | 1 | SPIKE | Completed | Security | In order to create a proper POC, the identity server must be able to authenticate, link, and create users for a google account; must support resource owner, implicit, and access token flows.
| Microsoft login | 1 | SPIKE | Completed | Security | In order to create a proper POC, the identity server must be able to authenticate, link, and create users for a Microsoft account; must support resource owner, implicit, and access token flows.
Sprint 3/4 | Impersonation | 1 | SPIKE | Completed | Security | In order to create a proper POC, resource servers must be able to filter and deny access to resources based on the user.
| WS-Federation + Windows login | 1 | SPIKE | To Do | Security | In order to create a proper POC, the identity server must be able to authenticate, link, and create users for a Windows account; must support resource owner, implicit, and access token flows.
| Partial Logins | 1 | SPIKE | To Do | Security | In order to create a proper POC, the identity server must be able to provide a page which allows users from an external provider to add missing claims; must support resource owner, implicit, and access token flows.
| Visual Studio 2017 Upgrade | 1 | Task | Completed | Technical Debt | In order to reduce code cost, the code base must work with visual studio 2017
| Angular 4 Upgrade | 1 | Task | Completed | Technical Debt | In order to reduce code cost, the gui must use angular 4
| POC - Nhibernate Stores | 1 | Task | Completed | Security | In order to integrate security, the POC must use Nhibernate to store the information
| POC - Angular 2 OIDC package | 2 | Task | Completed | Security | In order to integrate security, the POC must have an angular package which contains oidc components
| POC - Authorization Server | 8 | Task | Completed | Security | In order to integrate security, the POC must have an authorization server
| POC - Database Seeder | 2 | Task | Completed | Security | In order to integrate security, the POC must have a test data seeded in
| POC - Resource Server Extensions | 1 | Task | Completed | Security | In order to integrate security, the POC must have an extension method which allows resource servers to authenticate tokens against the authorization server
| POC - Access Code Extensions | 1 | Task | Completed | Security | In order to integrate security, the POC must have an extension method which allows clients using the access code to authenticate
| POC - Implicit Flow Module | 2 | Task | Completed | Security | In order to integrate security, the POC must have an angular 2 module which supports implicit flow
| POC - Resource Owner Flow | 3 | Task | Completed | Security | In order to integrate security, the POC must have an angular 2 module which supports the resource owner flow
| POC - External Provider | 1 | Task | Completed | Security | In order to integrate security, the POC must support external providers
| POC - Windows Federated STS | 3 | Task | Deferred | Security | In order to integrate security, the POC must have an extension method which allows a server to act as a Federated STS
| POC - Developer management | 5 | Task | Deferred | Security | In order to integrate security, the POC must have forms which allow 3rd parties to authenticate against it
Sprint 5 | .gitignore changes | 0 | Task | Completed | Technical Debt | Add packages/ to the .gitignore, so that if referencing a class dotnet project, binaries wont accidentally be uploaded to git.
| Bitwise Architecture Consistency | 0.5 | Task | Completed | Technical Debt | For each C# project, make sure the target CPU has the same value (preferably Any CPU), so that referencing projects does not cause build issues.
| .net Framework Consistency | 0.5 | Task | Completed | Technical Debt | For each .net project, have the .net framework be the same (net461), so that upgrading in the future will be less costly.
| Change folder for @lvl.core to front-end | 0.5 | Task | Completed | Technical Debt | Move the contents of @lvl.core to a directory called front-end, so that it can be found more easily in alphabetical order, and it has more relation to it's use.
| Change @lvl.typescript-generator folder | 0.5 | Task | Completed | Technical Debt | Move the contents of @lvl.typescript-generator to typescript-generator, so that it can be found more easily in alphabetical order.
| Change @lvl.typescript-generator.Tests folder | 0.5 | Task | Completed | Technical Debt | Move the contents of @lvl.typescript-generator.Tests to typescript-generator.tests, so that it can be found more easily in alphabetical order.
| Change lvl.DatabaseGenerator folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.DatabaseGenerator to DatabaseGenerator, so that it can be found more easily in alphabetical order.
| Change lvl.DatabaseGenerator.Tests folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.DatabaseGenerator.Tests to DatabaseGenerator.Tests, so that it can be found more easily in alphabetical order.
| Change lvl.Ontology folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.Ontology to Ontology, so that it can be found more easily in alphabetical order.
| Change lvl.Ontology.Tests folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.Ontology.Tests to Ontology.Tests, so that it can be found more easily in alphabetical order.
| Change lvl.Repository folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.Repository to Repository, so that it can be found more easily in alphabetical order.
| Change lvl.Repository.Tests folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.Repository.Tests to Repository.Tests, so that it can be found more easily in alphabetical order.
| Change lvl.Web folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.Web to Web, so that it can be found more easily in alphabetical order.
| Change lvl.Web.Tests folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.Web.Tests to Web.Tests, so that it can be found more easily in alphabetical order.
| Change lvl.TestDomain folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.TestDomain to TestDomain, so that it can be found more easily in alphabetical order.
| Change lvl.TestDomain folder | 0.5 | Task | Completed | Technical Debt | Move the contents of lvl.TestWebSite to TestWebSite, so that it can be found more easily in alphabetical order.
| Create Core Solution folder | 0.5 | Task | Completed | Technical Debt | Move all projects which are agnostic to a business process to a core solution folder, so that projects can be grouped by business process later.
| Fixing dotnet runner | 0.5 | Task | Completed | Technical Debt | Remove the custom dotnet runner, and replace it with the built in one, so that mantenance is decreased.
| Repository SQLite Bug Fixes | 0.5 | Task | To Do | Technical Debt | In the repository, insides transactions; add a lock to the transactions, so that asynchronous SQLite operations don’t end transactions before complete.
| Assembly Loader Bug Fixes | 0.5 | Task | To Do | Technical Debt
| Configuration Cleanup | 1 | Task | To Do | Technical Debt
| Console Logging | 2 | Task | To Do | Technical Debt
| Error Messages on Responses | 2 | Task | To Do | Technical Debt
| NHibernate Conventions | 5 | Task | To Do | Technical Debt
| Aggregate Pattern | 2 | Task | To Do | Technical Debt
| Database Migration Refactoring | 2 | Task | To Do | Technical Debt
| Refactor Angular CLI | 1 | Task | To Do | Technical Debt
| Correct Validation Factory | 0 | Task | To Do | Platform
| Style Architecture | 1 | Task | To Do | UX
| Core Module/Settings | 1 | Task | To Do | Technical Debt
| Storage Services | 1 | Task | To Do | Platform
| Header Services | 1 | Task | To Do | Security
| Api Services | 1 | Task | To Do | Platform
| Angular 2 Validation | 5 | Task | To Do | Platform
| Animations | 2 | Task | To Do | UX
| Common Layout | 3 | Task | To Do | Platform
| Oidc Seeder | 2 | Task | To Do | Security
| Nhibernate Identity Stores/Models | 3 | Task | To Do | Security
| Password Hashing/Authentication | 2 | Task | To Do | Security
| Cors Policy Service | 1 | Task | To Do | Security
| Authorization Server Extensions | 1 | Task | To Do | Security
| Token Service | 3 | Task | To Do | Security
| Abstract Security Service | 1 | Task | To Do | Security
| Resource Owner Security Service | 1 | Task | To Do | Security
| Resource Owner Login Form | 1 | Task | To Do | Security
| 3rd Party Login | 2 | Task | To Do | Security
| Data Authorization Filters | 2 | Task | To Do | Security
| Data Authorization Interceptor | 2 | Task | To Do | Security
| Resource Server Extensions | 1 | Task | To Do | Security
| Impersonation | 1 | Task | To Do | Security
| Embedded File Provider | 2 | Task | To Do | Security
| Mvc Angular build | 1 | Task | To Do | Security
| Implicit Client Extensions | 0.5 | Task | To Do | Security
| Implicit Security Service | 1 | Task | To Do | Security
| Implicit Login Form | 3 | Task | To Do | Security
| Consent Form | 2 | Task | To Do | Security
| Login Callback Form | 2 | Task | To Do | Security
| Developer Page | 5 | Task | To Do | Security
| Read Oauth Specification | 3 | SPIKE | To Do | Security | https://tools.ietf.org/html/rfc6749
| Continuous Integration - Big Picture | 1 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/continuous-integration-delivery-big-picture
| Continuous Integration | 1 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/continuous-integration
| NPM Continuous Integration | 3 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/javascript-development-environment
| DevOps | 2 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/implementing-devops-real-world
| Team City Getting Started | 3 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/teamcity-getting-started
| Team City psake | 2 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/continuous-integration-psake-teamcity-getting-started
| Continuous Delivery - Big Picture | 1 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/continuous-integration-delivery-big-picture
| Integrating Docker with DevOps | 1 | SPIKE | To Do | Build Server | https://app.pluralsight.com/library/courses/integrating-docker-with-devops-automated-workflows
| Windows Group Policy Fundemendals | 8 | SPIKE | Deferred | Security | https://app.pluralsight.com/library/courses/group-policy-fundamentals
| Linux User and Group Management | 3 | SPIKE | Deferred | Security | https://app.pluralsight.com/library/courses/lfcs-linux-user-group-management
| Securing ASP Api (chapter 3) | 2 | SPIKE | Deferred | Security | https://app.pluralsight.com/library/courses/implementing-restful-aspdotnet-web-api
| Securing multiple clients | 3 | SPIKE | Deferred | Security | https://app.pluralsight.com/library/courses/building-securing-restful-api-aspdotnet
| Client Management | 1 | SPIKE | Deferred | Security | In order to create a proper POC, the identity server must provide an interface to manage applications which are authenticating against it.
| Identity Server with Nhibernate stores | 1 | SPIKE | Deferred | Security | In order to create a proper POC, a simple identity server must be built which uses Fluent Nhibernate as a storage mechanism; it must support the resource owner flow.

## drop-downs
Type | Statuses | Themes
SPIKE | To Do | Security
Task | In Progress | Technical Debt
| Completed | Build Server
| Deferred | Platform
| Duplicate | UX